## Blank
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%

## Example
GANT CHART GROUP 3
PROJECT TITLE | Green Code Project
PROJECT LEADER | Mikkel Johannessen
GROUP NAME | Group 3
DATE | 2025-04-24
[7 empty] | SPRINT ONE | [14 empty] | SPRINT TWO | [14 empty] | SPRINT THREE | [14 empty] | SPRINT FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.1 | Project Management
1.1.1 | Charting | Team | 2025-01-15 | 2025-01-29 | 14 | 100%
1.1.2 | Planning | Team | 2025-01-15 | 2025-01-29 | 14 | 100%
1.1.3 | Requirements | Reidar | 2025-01-15 | 2025-01-29 | 14 | 100%
1.1.4 | Time management | Mikkel | 2025-01-15 | 2025-01-29 | 14 | 90%
1.1.5 | Reports | Team | 2025-01-15 | 2025-01-29 | 14 | 80%
1.1.6 | Meetings | Mikkel | 2025-01-15 | 2025-01-29 | 14 | 90%
1.1.7 | Documentation | Team | 2025-01-29 | 2025-04-29 | 90 | 90%
1.1.8 | Prototyping | Team | 2025-01-29 | 2025-03-07 | 37 | 100%
1.2 | Technical Design
1.2.1 | Front-end | - | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.1.1 | HTML | Jonathan + team | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.1.2 | CSS | Jonathan + team | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.1.3 | JavaScript | Patric + Team~ | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.2 | Back-end | - | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.2.1 | Database - Moved to backlog | Torjus, Mikkel, Vetle | 2025-02-05 | 2025-04-15 | 69 | X%
1.2.3 | Project Documents | - | 2025-02-05 | 2025-04-15 | 69 | 90%
1.2.3.1 | Pictures | Team | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.3.2 | Link | Team | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.3.3 | Tools | Team | 2025-02-05 | 2025-04-15 | 69 | 100%
1.2.3.4 | Files | Team | 2025-02-05 | 2025-04-15 | 69 | 100%
1.3 | Testing
1.3.1 | Unit testing | Full team | 2025-04-08 | 2025-04-24 | 16 | 100%
1.3.2 | System testing | Full team | 2025-04-08 | 2025-04-24 | 16 | 100%
1.3.3 | User acceptance testing | Full team | 2025-04-08 | 2025-04-24 | 16 | 100%
1.3.4 | Stress testing | Full team | 2025-04-08 | 2025-04-24 | 16 | 100%
1.4 | End
1.4.1 | Schedule | Mikkel | 2025-01-29 | 2025-04-22 | 83 | 95%
1.4.2 | Presenting | Full team | 2025-04-17 | 2025-04-29 | 12 | 50%
1.4.3 | User guide - Moved to backlog | Jonathan | 2025-04-10 | 2025-04-29 | 19 | X%
1.4.4 | Publishing | Full team | 2025-04-28 | 2025-04-29 | 1 | 100%
1.4.5 | Feedback | Anh, Team | 2025-01-29 | 2025-04-29 | 90 | 80%
1.4.6 | Final Report | Full team | 2025-01-29 | 2025-04-29 | 90 | 100%